## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | PRITHVIKA R | 2024-12-16 | Unable to fetch Data from API,Sandbox environments from bank | S2 | PRITHVIKA R | Maintainability | Resarched and tried with other limited bank and their sandbox environments | 2024-12-22 | closed | Fetched data from sandbox in json format
2 | PRITHVIKA R | 2024-12-20 | Oauth Framework and Tokenization( Building a secure environment Cloudinary) | S3 | PRITHVIKA R | User Interface | Ensured using ngork to avoid errors for completing | 2024-12-28 | closed | succesfully built an Oauth framework
3 | PRITHVIKA R | 2025-01-14 | Data aquisation via Web Scarapping | S8 | PRITHVIKA R | User Interface | Tried using beautifulsoap and selenium, but couldn't access most websites due to secured interface and also the chrome version didn't support, instead used yfinance and otther such python libraries to scrape and fetch data | 2025-01-17 | open | Requires further knowladge and experience to work with selenium and also the chrome version supporting
4 | PRITHVIKA R | 2025-01-06 | Errors with Ocr extraction | S5 | PRITHVIKA R | Standards | Included preprocessing techniques,that helped removing noice and extract accurately | 2025-01-25 | closed | Improved performance
5 | PRITHVIKA R | 2025-01-22 | Errors with LLM fine tuning | S12 | PRITHVIKA R | Standards | used training,testing with help of dictonary and mapping methods with shuffling and fed lage dataset | 2025-01-25 | closed | Improved performance

## Sheet2
Logical
User Interface
Maintainability
Standards
Others